## Project Data
Project Name | Project 2 - NIM - Automated Thematic Analysis
Online team meeting | https://fau.zoom-x.de/j/64229233763?pwd=MboXckMTe5aVIBRIwvO71OgqjXJ7zb.1
Production system (if any) | ...
Test system (if any) | ...
GitHub repository | https://github.com/amosproj/amos2026ss02-automated-thematic-analysis
GitHub feature board | https://github.com/orgs/amosproj/projects/98
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/102
Position of T-shirt logo | Upper Torso Right Small
Link to logo for black T-shirt | https://github.com/amosproj/amos2026ss02-automated-thematic-analysis/blob/main/Deliverables/sprint-01/team-logo.svg
Link to logo for white T-shirt | https://github.com/amosproj/amos2026ss02-automated-thematic-analysis/blob/main/Deliverables/sprint-01/team-logo.svg
Additional materials | ...
Team mailing list | oss-amos-proj2@lists.fau.de (Emails sent here get quarantined by the TU Berlin Spam Filter)

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Kahvecioglu | Selin | slnkahveci | kahvecioglu@campus.tu-berlin.de
de Sa Filho | Fabiano | fdesafilho | fabiano.de.sa@fau.de
Ammann | Paul | Wecoreator | p.ammann@campus.tu-berlin.de
Schmidt | Alexander | alexanderschmi | a.schmidt.2@tu-berlin.de
Wendlandt | Julian | julianlucawendlandt-jpg | julian.luca.wendlandt@campus.tu-berlin.de
Müermann | Ole | ClimbTheGrind | ole.mueermann@fau.de
Klarer | Paul | paulKlarer | paul.linus.klarer@fau.de
Mantsch | Christoph | Christoph-Mantsch | christoph.cm.mantsch@fau.de
Annus | Mohammad | annus3 | mohammad.annus@fau.de
Rasul | Hamid | hrasul | hamid.rasul@fau.de

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | Comment
1 | 2026-04-15 | Alexander Schmidt | Fabiano de Sa Filho | Everyone else | N/A | Christoph Mantsch
2 | 2026-04-22 | Alexander Schmidt | Fabiano de Sa Filho | Everyone else | Paul Klarer | Christoph Mantsch
3 | 2026-04-29 | Fabiano de Sa Filho | Alexander Schmidt | Everyone else | Paul Klarer | Christoph Mantsch
4 | 2026-05-06 | Alexander Schmidt | Fabiano de Sa Filho | Everyone else | Selin Kahvecioglu | Christoph Mantsch
5 | 2026-05-13 | Alexander Schmidt | Fabiano de Sa Filho | Everyone else | Ole Müermann | Christoph Mantsch
6 | 2026-05-20 | Fabiano de Sa Filho | Alexander Schmidt | Everyone else | Ole Müermann | Christoph Mantsch
7 | 2026-05-27 | Alexander Schmidt | Fabiano de Sa Filho | Everyone else | Hamid Rasul | Christoph Mantsch | Mid-term due
8 | 2026-06-03 | Fabiano de Sa Filho | Alexander Schmidt | Everyone else | Selin Kahvecioglu | Christoph Mantsch
9 | 2026-06-10 | Alexander Schmidt | Fabiano de Sa Filho | Everyone else | Hamid Rasul | Christoph Mantsch
10 | 2026-06-17 | Fabiano de Sa Filho | Alexander Schmidt | Everyone else | Paul Ammann | Christoph Mantsch
11 | 2026-06-24 | Alexander Schmidt | Fabiano de Sa Filho | Everyone else | Mohammad Annus | Christoph Mantsch
12 | 2026-07-01 | Fabiano de Sa Filho | Alexander Schmidt | Everyone else | Mohammad Annus | Christoph Mantsch
13 | 2026-07-08 | Alexander Schmidt | Fabiano de Sa Filho | Everyone else | Paul Ammann | Christoph Mantsch
14 | 2026-07-15 | Fabiano de Sa Filho | Alexander Schmidt | Everyone else | Julian Wendlandt | Christoph Mantsch | Demo day!
15 | 2026-07-22 | Alexander Schmidt | Fabiano de Sa Filho | Everyone else | Julian Wendlandt | Christoph Mantsch | Retrospective
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here
Formulas:
Meeting Day = [Meeting Day, row above]+7

## Team Contract
Goals | Having Fun
Satisfy NIM
Program an automated thematic analysis of interview transcripts
Meeting norms | Joining the meeting is mandatory
Always be on time (up to 10 min late is fine if short message on discord)
Follow the timeline
Take notes in each meeting
Happiness Index after Sprint retrospective
Each meeting takes 1:30 hours
Working norms | Tell us if/when you are working on a task
We encourage pair programming
Coordination norms | Self assign issues you are opening
Do not force push
Use PEP 8 as style (configure your IDEs)
Follow https://www.atlassian.com/git/tutorials/comparing-workflows/gitflow-workflow
Once every workday check discord
If someone is blocked share with the team
Communication norms | Criticism should be productive
Language should be respectful at all time (written and oral)
Consideration norms | Discuss disagreement openly
Follow the NDA and data privacy
Try not to induce bias in our project
Cont. improvement norms | Finish work until tuesday evening 20:00 PM
At the end of the meeting discuss happyness score / what could be done better / what was good
Rewards | Have a happy meeting
Sanctions | Write a poem saying you are sorry
After multiple or serious offenses escalate to prof
Signatures
Scrum Master | Christoph Mantsch
Product owner | Alexander Schmidt
Product owner | Fabiano de Sa Filho
Software developer | Ole Müermann
Software developer | Julian Wendlandt
Software developer | Hamid Rasul
Software developer | Paul Klarer
Software developer | Paul Ammann
Software developer | Selin Kahvecioglu
Software developer | Mohammad Annus

## Product Goal
Product Vision | Project Mission
LLMs are a fantastic tool to interview research subjects at scale, which previously had to be done by human researchers. This method generates unstructured interview dialogues which must then be processed and analysed manually. The goal of this project is to use LLMs to also automate the analysis part, enabling policy researchers to feed their interview corpus to our tool and obtain not only the thematic analysis, but also relevant insights derived from the demographic data of the respondents. This way, we seek to bridge the gap between quantitative and qualitative policy research. | To engineer a secure, open-source tool that ingests thousands of subject interviews about a policy topic and produces an accurate thematic analysis breakdown. The core is a multi-stage LLM pipeline that extracts quotes, codes them into themes, clusters and ranks those themes, and cross-references them against respondent demographic dimensions. Results are surfaced through a lightweight frontend and exportable in structured formats. We also provide direct reference back to the corpus, so researchers can see which interviews most strongly manifest a particular theme or demographic combination. We build on QuaLLM by incorporating this demographic layer, inferring how discovered themes distribute across the profile of research subjects, and surfacing patterns that a purely manual process would likely miss.

## Product Glossary
Term | Definition
Corpus / Dataset | The 1,058 LLM-led interviews on the economic impact of AI provided by the Industry Partner. Format: JSON
Demographic Data | Categorical variables describing each subject in the Corpus; has been partially sanitized by Industry partner, but must be handled with care. Absolutely should not be downloaded or uploaded to third parties. Format: CSV
Thematic Analysis | The qualitative method of identifying and analyzing patterns of meaning (themes) in a dataset. These themes should be followed by a short description and some quantitative measures of prevalence in the dataset.
QuaLLM | The specific LLM-based framework serving as the baseline architecture for our project. Suggested by Dr. Kaiser, can be seen on Rao et al.

## Sprint Goals
Sprint # | Sprint goal
1 | Meeting with industry partner, designing the logo, setting up the project
2 | Ingesting the interview dataset provided by the industry partner, working on the Architecture Description document, and delivering a first prototype that successfully passes text through a basic LLM endpoint.
3 | Creating a basic demo to be shown to Dr. Kaiser. Starting with simple views, database and llm communication
4 | Creating the first version of the frontend, finishing up the basic demo of the backend. Adding a Readme and writting a proper Build script.
5
6
7
8
9
10
11
12
13
14
15

## Velocity Tracking
Sprint # | Story Points Realized
1 | N/A
2
3
4
5
6
7
8
9
10
11
12
13
14
15
PLEASE CREATE THE VELOCITY CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 0 | 0
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
... |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 0 | 0
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
... |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done

## Documentation
Type | Link / reference

## Bill of Materials
# | Context | Name | Version | License | Comment
1 | Database | PostgreSQL | 18 | PostgreSQL License | Reliable open-source relational database for structured application data.
2 | Database extension | pgvector | 0.8 | PostgreSQL License | Adds vector storage and similarity search directly inside PostgreSQL
3 | Programming language / runtime | Python | 3.11 | Python Software Foundation License Version 2 | Core runtime for backend
4 | Database ORM / SQL toolkit | SQLAlchemy | 2 | MIT | Provides Python ORM and SQL toolkit support for database access and queries.
5 | Backend API framework | FastAPI | 0.136 | MIT | Build easy python basd APIs
6 | Data validation | Pydantic | 2.13 | MIT | Validates, parses, and serializes Python data models safely.
7 | LLM application framework | LangChain | 1.2 | MIT | Build LLM workflows
8 | NLP library | spaCy | 3.8 | MIT | Provides production-ready NLP features such as tokenization, NER, and pipelines. Contains e.g. BERT Implementations for NLP tasks like classification
9 | ASGI server | Uvicorn | 0.46 | BSD-3-Clause | Runs the FastAPI backend
10 | PostgreSQL async driver | asyncpg | 0.31 | Apache License 2.0 | Provides fast asynchronous PostgreSQL connectivity for Python services.
11 | LLM observability | Langfuse | 4.5 | MIT Expat for core; enterprise directories under separate ee/LICENSE | Tracks LLM traces, prompts, latency, costs, and evaluation data.
12 | HTTP client | HTTPX | 0.28 | BSD-3-Clause | Provides sync and async HTTP calls to model APIs and backend services.
13 | Testing framework | pytest | 9 | MIT | Automated Testing
14 | Environment configuration | python-dotenv | 1.2 | BSD-3-Clause | Loads local environment variables from .env files during development.
15 | Tokenization | tiktoken | 0.12 | MIT | Counts and encodes tokens. Used by LangChain for Textsplitting.
16 | LLM frontend prototyping | Streamlit | 1.56 | Apache License 2.0 | Quickly builds Python-based web apps, dashboards, and chat prototypes for LLM applications. Used for protoyping & early previews.
17 | Large language model | Gemma | Gemma 4 31B | Apache License 2.0 | Candidate self-hosted open model. More details in the model selection document. Final model decision is still outstanding.
18 | Large language model | Qwen | Qwen3.5-35B-A3B | Apache License 2.0 | Candidate self-hosted open model. More details in the model selection document. Final model decision is still outstanding.
19 | Large language model | Mixtral | Mixtral 8x7B | Apache License 2.0 | Candidate self-hosted open model. More details in the model selection document. Final model decision is still outstanding.
20 | LLM gateway / provider abstraction | LiteLLM | 1.83 | MIT for OSS package; enterprise package/features under separate commercial license | Provides a unified OpenAI-compatible interface for calling multiple LLM providers.
21 | Containerization / deployment | Docker Engine | 29 | Apache License 2.0 | Packages and runs the application stack consistently across environments.
22 | Web framework | Flask | 3.1 | BSD-3-Clause | Server-side web framework for the production frontend
23 | Template engine | Jinja2 | 3.1 | BSD-3-Clause | Template engine used with Flask to generate server-rendered HTML views
24 | Chat / users | OpenWebUI | 0.9 | Open WebUI License | chat-style interaction and user management. Current OpenWebUI versions use the Open WebUI License, which is based on BSD-3-Clause but adds a branding / attribution restriction

## Planning Poker
Last Name | First Name | Value
Kahvecioglu | Selin |  | #DIV/0! | #DIV/0!
de Sa Filho | Fabiano
Ammann | Paul
Schmidt | Alexander
Wendlandt | Julian |  | 0 | No size
Müermann | Ole |  | 1 | Trivial size
Klarer | Paul |  | 2 | Small size
|  |  | 3 | Medium size
Annus | Mohammad |  | 5 | Large size
Rasul | Hamid |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value